## Summary
INTERNAL ENGINEERING AUDIT · NOT FOR EXTERNAL DISTRIBUTION
Program — Production-Readiness Audit (Refresh)
A code-verified re-audit of the MERN e-learning MVP, checked against main plus the two open PRs from this session.
Repo | program-merged-update
Baseline | main @ a9de741 (this audit's predecessor was main @ eaa5950)
Compared against | origin/fix/admin-course-management-filter-crash (PR #92) + origin/feature/home-explore-instructor-profiles (PR #93), merged locally into a scratch branch for verification — neither is merged into main yet
Date | 28 Jul 2026
Method | direct code read + live browser testing + automated integration/smoke suites, re-run against the combined PR state
EST. COMPLETION (live formula — Done=1.0, Partially Done=0.5, Broken/Not Started=0)
Counts (of all items tracked on the 'All Items' sheet):
Done
Fixed This Session
Partially Done
Broken
Not Started
Bottom line
The Home/Explore/Instructor-profile feature (PR #93) is genuinely wired end-to-end — verified live against the real dev database, not just the build. The admin Course Management crash (PR #92) is fixed. But neither PR touches the two CRITICAL pre-existing blockers this audit's predecessor found: the isActive crash still takes down the Learning Portal for any course with lessons, and Cloudinary uploads are still unverified/broken in this environment. A separate, un-fixed bug in the same admin file (Approve sets status:'published', not 'approved') still makes approved courses vanish from the list until refresh — do not mistake the PR #92 fix for a fix of that bug, they are different bugs in the same file. Net: forward progress on two fronts, zero regressions found, but the pre-existing severe issues are exactly as severe as before.
What changed since the last audit (commit eaa5950 → this session)
+ New: personalized Home page (major/semester rows), rebuilt Explore page (category tabs + instructor search), public instructor profile system. Verified live in a real browser against the dev DB.
+ New: major field on User (Register + Settings); optional major/semester on Course.
+ Fixed: Admin > Course Management crashed (ReferenceError: setSelectedIds is not defined) on every status-tab click — found incidentally, fixed, verified.
+ Fixed: login/register only returned a minimal user object, so a newly-set major didn't reflect on Home until next page load — now hydrates via /auth/me immediately.
! NOT fixed, still open: isActive crash (LearningPortal.jsx), Cloudinary placeholder credentials, approve-sets-'published' bug (AdminCourseManagementTab.jsx), fake CheckoutPage payment UI + mock identity, fake-success UI cluster, System Management demo shell, no CI/CD, no deployment.

## All Items
All Items — flat list, source of truth for the Summary sheet's live completion score |  |  |  | completion formula ->
Edit the Status column (Done / Partially Done / Broken / Not Started / Fixed This Session) and the Summary % recomputes automatically.
Category | Item | Status | Notes
Student | Register (role selector) | Done | Unchanged. Real role picker, backend sanitizes role.
Student | Browse / search courses | Done | Split across the new Home page (personalized) and new Explore page (category tabs + search) — capability preserved and extended, not regressed.
Student | View course details | Done | Unchanged. Real GET /courses/:id.
Student | Enroll | Partially Done | Unchanged. Still wrapped in a fully-built fake payment UI (CheckoutPage.jsx) with hardcoded mock identity.
Student | Watch video lessons | Broken | UNCHANGED — still crashes. Undefined `isActive` at LearningPortal.jsx:473-474 (should be `isCurrent`, declared line 417). Not touched by either PR this session.
Student | Mark lesson complete | Done | Unchanged. Real endpoint, but unreachable in practice — blocked by the crash above.
Student | See progress | Done | Unchanged. Server-computed.
Instructor | Register as instructor | Done | Unchanged.
Instructor | Dashboard | Done | Unchanged.
Instructor | Create course | Done | Enhanced this session: category is now a 10-option curated dropdown (was 4 hardcoded values), plus new optional Major/Semester fields. Verified live end-to-end (create → approve → appears correctly in Home/Explore).
Instructor | Add lesson + video upload | Broken | UNCHANGED (environment-specific). Cloudinary creds in server/.env are still literal placeholders (your_api_key). Not touched this session.
Instructor | Submit for approval | Done | Unchanged. Every new course is created pending by design.
Admin | Login | Done | Unchanged.
Admin | Dashboard stats | Partially Done | Unchanged. AdminOverviewTab.jsx:51-59 still has hardcoded fallback numbers masking genuine zero-values.
Admin | View pending courses | Done | Unchanged.
Admin | Approve / reject | Partially Done | One bug in this feature fixed this session (see 'Course Management functionality' below), but a DIFFERENT bug remains open: handleApprove sets status:'published' (AdminCourseManagementTab.jsx:196), which matches neither the Approved nor Pending filter — course vanishes until manual refresh. Reject still sends a hardcoded reason string, no real reason UI.
Recent UI/UX | Static pages / footer | Done | Unchanged.
Recent UI/UX | Courses nav dropdown | Done | SUPERSEDED this session — the sidebar's category dropdown (COURSE_CATEGORIES constant + courses-nav-dropdown) was removed entirely and replaced by the new Explore page's in-page category tabs (data-driven, 10 curated categories + Instructors + All). Category filtering capability preserved and expanded, not regressed.
Recent UI/UX | Loading animations | Done | Unchanged.
Recent UI/UX | Admin Quick Actions removal | Done | Unchanged.
Recent UI/UX | User Management consolidation | Done | Unchanged.
Recent UI/UX | Course Management functionality | Partially Done | IMPROVED this session: the status-filter-tab crash (setSelectedIds is not defined — orphaned bulk-select leftover, no matching state or UI anywhere in the file) is FIXED and verified live. Still Partially Done overall because the separate approve-status-value bug (see Admin > Approve/reject) remains in the same file.
Recent UI/UX | Certificates removal | Done | Unchanged.
Recent UI/UX | Financial Management cleanup | Done | Unchanged.
Recent UI/UX | Superadmin profile removal | Done | Unchanged.
New This Session | Major field (Register + Settings) | Done | New. Added to User model, Register step 2 (student branch), and Settings > Account. Verified live: setting it at registration now reflects on Home immediately (see the /auth/me hydration fix below).
New This Session | Home page personalization | Done | New. Repurposes the old generic Explore catalog (client/src/components/ExploreTab.jsx) into a per-semester, horizontally-scrollable feed driven by the student's major. Graceful fallback (general catalog + prompt) when no major is set. Verified live end-to-end with a real created/approved course.
New This Session | Explore page rebuild | Done | New (client/src/components/DiscoverTab.jsx, mounted at /student/explore). Data-driven category tabs (10 curated categories + All + Instructors), combined course/instructor search, instant client-side filtering. Verified live.
New This Session | Instructor profile system | Done | New. GET /api/instructors (list/search) + GET /api/instructors/:id (profile), and client/src/components/InstructorProfilePage.jsx at /instructor/:id. Bio/expertise derived from existing goalsText/course-category data — no new PII fields. Verified live: avatar, bio, expertise tags, rating, student count, and course grid all render correctly.
New This Session | Admin Course Management crash fix | Fixed This Session | Found incidentally while manually verifying the above. setSelectedIds(new Set()) was called on every status-filter-tab click with no corresponding useState anywhere in the file (dead leftover from a removed bulk-select feature) — threw a ReferenceError and crashed the tab. Fix: removed the orphaned call. This is PR #92, open, not yet merged to main.
New This Session | /auth/me hydration after login/register | Fixed This Session | Found while testing the major field: login/register responses only ever returned a minimal user object (id/name/email/role/avatarUrl), so a freshly-set major (or any other profile field) didn't show up until the next page load. Now App.jsx calls GET /auth/me right after login/register to hydrate the full profile immediately.

## Security
Security — re-read every route file + core auth/crypto/sanitization middleware, plus the new instructor endpoints and Course/User schema additions
Items unchanged from the previous audit are marked accordingly; new rows cover what this session actually added.
Area | Status | Detail
Cookies | Verified — Unchanged | httpOnly always; secure/sameSite=none only in production. Correct.
Password hashing | Verified — Unchanged | bcrypt cost 12, field excluded from queries by default (select:false).
JWT secret | Verified — Unchanged | Read from env, never hardcoded.
Authorization | Verified — Unchanged | Every route file checked incl. the two new instructor routes. protect/authorize(...) correctly gates every mutating route; ownership checks present on every instructor mutation.
New: public instructor endpoints | Verified — Safe | GET /api/instructors and GET /api/instructors/:id are intentionally public (profile pages), and correctly scope returned fields — listInstructors uses .select('name lastName avatarUrl goalsText') (no email/PII); getInstructorProfile fetches the full User doc internally but manually constructs the JSON response field-by-field, so nothing beyond name/lastName/avatarUrl/bio/derived stats ever leaves the server.
New: major/semester/category input | Verified — Safe | All new Course/User fields (major, semester, and the expanded category set) pass through the existing global mongoSanitizeMiddleware + xssSanitizeMiddleware (app.js, applied before all routes) — no new injection surface introduced.
New: instructor-name search | Verified — Safe | GET /courses?search= now also regex-matches instructor name via mongoose.model('User').find(...) — uses the same escapeRegex() utility as the existing title search, so no ReDoS/regex-injection regression.
New: rate limiting coverage | Verified — Safe | The two new /api/instructors routes are mounted after app.use(globalApiLimiter) in app.js, so they inherit the global backstop like every other route. No dedicated limiter needed for public GETs at this scale.
New (minor gap): Course.semester has no bounds | Minor Gap | semester is a plain Number with no min/max/enum validation — an instructor could set 0, -5, or 9999. Not a security issue (no injection, no auth bypass); worst case is a course that silently never appears in any Home semester row. Worth a follow-up validation pass, not urgent.
Video URL gating | Verified — Unchanged | Public course endpoint excludes videoUrl; gated lesson endpoint checks enrollment/ownership/admin. One pre-existing minor inconsistency carried forward: an isAdmin check on the course-details endpoint (courseController.js:254) only tests role==='admin', not 'superadmin'.
Rate limiting (pre-existing) | Verified — Unchanged | Real limits on login/register/check-email + global backstop. forgot-password and OTP limiters remain defined but never wired to any route — dead scaffolding for an explicitly out-of-scope feature.
Input sanitization | Verified — Unchanged | Mongo-operator stripping + XSS escaping applied globally, layered with express-validator on auth routes.
CORS | Verified — Unchanged | Correct env-driven allowlist implementation; still never exercised against a real production domain because nothing is deployed.
Unmerged security branch | Unchanged — Still Unmerged | origin/feature/enterprise-security(sprint2) still exists on the remote, still not merged into main. Diff not read this session either — if it holds intended fixes for this release, they are still not in main.

## Bugs & Known Issues
Bugs / Known Issues — re-verified against the combined PR state; new rows for what was found/fixed this session
Issue | Severity | Status | Detail
Undefined isActive crashes the Learning Portal | CRITICAL | Open — Unchanged | LearningPortal.jsx:473-474. Confirmed still present, still undeclared in scope — the correct variable (isCurrent) is declared two lines above at 417 but the wrong name was used at 473-474. Throws a ReferenceError on any course with lessons. One-line fix, not made this session — out of scope for the Home/Explore/Instructor-profile work.
Cloudinary uploads non-functional | CRITICAL | Open — Unchanged | server/.env still has literal placeholder credentials (CLOUDINARY_API_KEY=your_api_key etc.). Not re-tested live this session; config confirmed unchanged.
Approved courses vanish from the admin list | MODERATE | Open — Unchanged (different bug than the one fixed this session) | AdminCourseManagementTab.jsx:196 — handleApprove sets status:'published', which matches neither the 'Approved' nor 'Pending' filter tab. Still present. Do not confuse with the crash fixed this session (below) — same file, different bug.
Admin Course Management: filter-tab crash | CRITICAL (now fixed) | FIXED This Session | PR #92. Clicking any status filter tab called setSelectedIds(new Set()) with no matching useState anywhere in the file — orphaned leftover from a removed bulk-select feature, no checkboxes or bulk toolbar exist. Threw a ReferenceError and crashed the tab on every click, blocking admins from filtering OR approving/rejecting courses at all. Verified fixed live: status tabs, detail panel, and Approve Course button all work without error.
Hardcoded mock identity shown at checkout | MODERATE | Open — Unchanged | client/src/data.js's fake user (real-looking name/email) still displayed to every user in CheckoutPage instead of the actual logged-in account.
Cluster of fake-success UI | MODERATE | Open — Unchanged | Report issue (console.log + toast only), Share (no clipboard call anywhere in the codebase), admin Export CSV (toast only, zero export logic), lesson Draft/Published toggle (handleTogglePublish only shows a toast, no API call, no state change), backend send-test-email endpoint (setTimeout(800) + hardcoded success). All confirmed still fake.
System Management is mostly a demo shell | MINOR | Open — Unchanged (not touched) | Not re-verified line-by-line this session since neither PR touches SystemManagement.jsx; carried forward from the prior audit at face value.
Build & lint | MINOR | Open — Slightly Changed | Build: still clean, zero errors, main JS bundle now 1.06 MB / 277 KB gzip (was 1.04 MB / 273 KB gzip — the new pages/components added ~20KB gzip). Lint (oxlint): 0 errors, 81 warnings counted this session (was '~45' estimated previously — different tooling run, not a like-for-like delta). All warnings are pre-existing patterns (unused vars/imports, missing hook deps); every new file added this session (DiscoverTab, InstructorCard, InstructorProfilePage, instructorController, instructorRoutes, majors.js, exploreCategories.js) has zero lint warnings.
Course.semester has no bounds validation | MINOR (new) | Open — New Finding | Introduced this session as part of the major/semester feature. No min/max/enum on the Course model's semester field. Not exploitable, just a data-quality gap — see Security sheet.

## Testing
Testing — re-run this session against the combined PR #92 + PR #93 state
Check | Result | Detail
Integration suite (server/test-integration.js) | Passed | Ran directly against the combined-branch worktree, in-memory MongoDB. All assertions passed — regression-clean.
New smoke test (major/semester/instructor endpoints) | Passed | Purpose-built this session, in-memory MongoDB: major/semester filtering on GET /courses, instructor-name search + avatar populate, GET /instructors aggregation (courseCount/avgRating/totalStudents/expertise), GET /instructors/:id (bio from goalsText, course list), 404 for non-instructor ids, PATCH /auth/profile major update, GET /auth/me allowlist. All passed.
Client build | Passed | npm run build in client/ — zero errors, on the true combined-PR state (not just each PR individually).
Manual QA — student | Done This Session | Registered a real student via the browser, picked a major at registration, confirmed Home personalizes immediately (no refresh needed), confirmed Explore category tabs filter instantly, confirmed Explore Instructors tab renders.
Manual QA — instructor | Done This Session | Registered a real instructor via the browser, created a course with the new category/major/semester fields, confirmed the form and submission work end-to-end.
Manual QA — admin | Done This Session | Logged in as an admin, navigated Course Management, switched status filter tabs (confirmed the crash fix), opened a course detail panel, approved a pending course, confirmed it moved to Approved and the API reflects it.
Manual QA — cross-role verification loop | Done This Session | Closed the loop: approved course confirmed visible on the student's Home page (correct semester row) and Explore page (correct category), and its instructor byline correctly links to a working instructor profile page.
Real Cloudinary upload | Not Verified (Unchanged) | Not re-tested this session — known broken per the Bugs sheet, out of scope for this work.
Full structured QA pass over every role's entire UI | Not Confirmed Done | This session's manual QA was substantial but targeted at the new feature area, same caveat as the previous audit: not a structured click-through of every existing screen.

## Deployment & Scope
Deployment Readiness & Scope Check — both unchanged since neither PR touches infra or scope-boundary features
Item | Status | Detail
Persistent deployment | Not Deployed — Unchanged | Still no GitHub Deployments/Pages/repo homepage/Dockerfile/vercel.json/render.yaml/Procfile/netlify.toml. Confirmed absent again this session.
CI/CD | Absent — Unchanged | Still no .github/workflows directory. Nothing runs tests or a build check automatically — confirmed again: two PRs were opened this session and nothing blocks a broken one from merging.
.env.example port drift | Open — Unchanged | server/.env.example still defaults PORT=5000; actual local dev value is 5050. Confirmed unchanged.
CORS/cookies for real prod domains | Unverified — Unchanged | Code is written correctly to support this; still never exercised against an actual production domain since nothing is deployed.
Hardcoded dev-only data in CheckoutPage | Open — Unchanged | client/src/data.js mock data still imported live.
Scope Check
Item | Status | Detail
Payments / Stripe | Out of Scope, Violated by UI | Unchanged. No real processor integration (zero references), but the fully-built fake payment UI (unwired buttons, '100% secure...30-day money-back guarantee' copy — confirmed still present at CheckoutPage.jsx:304) is still live and reachable, directly contradicting the written no-fake-payment-simulation instruction.
Live chat / gamification / wishlist / certificates | Confirmed Absent — Unchanged | Re-grepped: zero functional references. Only stale doc mentions / false-positive 'badge' UI hits, same as before.
Mobile app | Correctly Scoped — Unchanged | Honest 'coming soon' static page.
Forgot password | Correctly Not Implemented, Dead Scaffolding Remains | Confirmed unchanged: the link is still a bare <a> with no href/onClick (AuthPage.jsx:476), and the forgot-password/OTP rate limiters are still defined but wired to nothing.

## Punch List
Prioritized Punch List — carried forward, re-ordered to reflect what this session actually resolved
In order — each item assumes the ones above it are done. Items marked 'DONE THIS SESSION' can be struck from future lists.
# | Item | Status | Detail
1 | Fix the isActive crash in LearningPortal.jsx | STILL OPEN | Unchanged — blocks core functionality, almost certainly a one-word fix (isActive → isCurrent). Do this first, same as last audit.
2 | Get real Cloudinary credentials into a real environment and verify upload end-to-end | STILL OPEN | Unchanged — currently unverified/broken, blocks everything downstream of course creation.
3 | Fix the approve-course status bug ('published' → 'approved') in AdminCourseManagementTab.jsx | STILL OPEN | Unchanged — do not confuse with item 4.
4 | Fix the crash when switching Course Management status filter tabs | DONE THIS SESSION (PR #92, unmerged) | setSelectedIds orphaned call removed. Merge PR #92 to close this out for real.
5 | Decide the fate of CheckoutPage — replace with a plain enroll flow, or explicitly scope in real payments | STILL OPEN | Unchanged.
6 | Remove the hardcoded mock identity from CheckoutPage (client/src/data.js) | STILL OPEN | Unchanged.
7 | Triage System Management's placeholder tabs and dead toggles | STILL OPEN | Not re-verified line-by-line this session; carried forward.
8 | Fix or remove the fake-success UI cluster | STILL OPEN | Unchanged.
9 | Stand up an actual deployment (staging at minimum) | STILL OPEN | Unchanged.
10 | Add CI | STILL OPEN | Unchanged — more relevant than ever: two more PRs (#92, #93) were opened this session with nothing to gate them.
11 | Merge PR #93 (Home/Explore/Instructor profiles) after review | NEW THIS SESSION | Verified live end-to-end this session; ready for review. Depends on nothing else in this list.
12 | Validate Course.semester bounds server-side | NEW THIS SESSION (minor) | Small follow-up — no min/max/enum on the new semester field.
13 | Clean up the rest — dead forgot-password scaffolding, dead admin reject-reason code path, .env.example port drift, stale certificate doc mentions, bundle-size warning | STILL OPEN | Unchanged.