## Summary
INTERNAL ENGINEERING BACKLOG · NOT FOR EXTERNAL DISTRIBUTION
Program — Master Backlog
Every remaining known item across web dev, security, backend, i18n, testing, deployment, and open PRs — code-verified against current main, not copied from stale docs.
Repo | program-merged-update (omar-abdelazim-dev/program)
Baseline | main @ f2b0bb6 (30 Jul 2026) — includes PR #92, #93, #94, #101, #102, #105, #107, #109, #110, merged and conflict-reconciled this session
Predecessor audit | production-readiness-audit-v2.xlsx, baseline main @ a9de741 — this workbook re-verifies every item from it against the current codebase and adds everything found/opened since
Method | Direct code read of current main + git diff/show against open PR branches + gh issue/pr list + full npm audit incl. devDependencies (client & server) + a dedicated route-level auth/CSRF/upload-validation/error-handling sweep + re-verification of every item the predecessor audit flagged as open
Date | 05 Aug 2026
Bottom line
The i18n/RTL/CMS PR stack (#101,102,105,107,109,110) plus the admin light-mode/lesson-approval PR (#94) are now merged and reconciled — that work is real and I build/test-verified it live. But three CRITICAL pre-existing bugs from the predecessor audit are still exactly as broken as before, untouched by any of this session's merges: the isActive crash that takes down video lesson viewing, placeholder Cloudinary credentials blocking all uploads, and the approve-course status-value bug that makes approved courses vanish from the admin list. This session also found a live security regression (login rate limit gutted 5→5000/15min) and a silent revenue-split regression in the still-open PR #111 — do not merge it as-is. Four dependency vulnerabilities (npm audit, incl. devDependencies) are outstanding, all with non-breaking fixes available except react-router. A dedicated sweep this session confirmed the core auth/CSRF/upload/error-handling foundation is genuinely sound: every mutating route is gated, CSRF double-submit is real and enforced, file uploads are size/mimetype validated, production errors never leak internals, and no secrets have ever been committed. There is still no CI/CD and no deployment anywhere, so nothing currently blocks a broken PR from being merged by hand.
Counts by priority (Master Backlog sheet)
Critical
High
Medium
Low
Total tracked items

## Master Backlog
Every backlog item currently known — web dev, security, backend, i18n, testing, deployment. Filter/sort freely; each row is independent.
# | Category | Item | Priority | Status | Source | Detail
1 | Security | Login rate limiter gutted (5 → 5000 attempts/15min) | Critical | Blocked | PR #111 (unmerged) | server/config/security.js changes RATE_LIMITS.login.max from 5 to 5000, effectively disabling brute-force protection on /api/auth/login. Confirmed via diff against main. Must be reverted before this PR can merge under any circumstances.
2 | Security | Revenue-split logic silently ignores admin-configured commission | High | Needs decision | PR #111 (unmerged) + Issue #62 | enrollmentController.js previously read SystemConfig.financial.commission (admin-configurable via the Commission Slider in System Management, default 15% platform/85% instructor). PR #111 replaces this with hardcoded 70/30 and 85/15 splits, making the Commission Slider UI silently non-functional. Needs a product decision, not a silent merge.
3 | Security | Dependency vulnerability: ip-address (server) | High | Open | npm audit (server) | High-severity SSRF/trust-boundary bypass in the ip-address package (leading-zero octet decoding). Fix available via `npm audit fix` (non-breaking).
4 | Security | Dependency vulnerability: brace-expansion (server, dev dependency) | High | Open | npm audit (server, full — including devDependencies, missed in the first pass) | High-severity DoS via unbounded expansion length causing an out-of-memory crash. Dev-tooling only, not shipped to production, but still a real supply-chain risk in CI/local dev. Fix available via `npm audit fix` (non-breaking).
5 | Security | Dependency vulnerability: postcss (client, dev dependency / build tooling) | High | Open | npm audit (client, full — including devDependencies, missed in the first pass) | High-severity path traversal via sourceMappingURL auto-loading, can disclose arbitrary .map files. Build-tooling only (not shipped to the browser bundle), but worth fixing. Fix available via `npm audit fix` (non-breaking).
6 | Security | JWT sign/verify don't pin an explicit algorithms allowlist | Low | Open | Checked this session | server/utils/generateToken.js and authMiddleware.js call jwt.sign()/jwt.verify() without an explicit `algorithms: ['HS256']` option. Modern jsonwebtoken versions handle this reasonably by default and the secret is never exposed, so this isn't an active exploit path — but pinning the algorithm explicitly is a standard OWASP-recommended hardening step and costs nothing to add.
7 | Security | Dependency vulnerability: react-router / react-router-dom (client) | High | Open | npm audit (client) | High-severity CSRF bypass in RSC mode. Fix requires `npm audit fix --force` (downgrades to react-router-dom@7.11.0, a breaking change) — needs a regression pass on routing after upgrading.
8 | Security | PR #82 — Advanced Auth / Refresh Tokens / Session Hardening is unmerged and now conflicting | High | Blocked | PR #82 (open) | Real security value: refresh token rotation (SHA-256 hashed at rest), account lockout after 5 failed logins, per-device session tracking + remote revoke, password-change global session invalidation, CORS 403 hardening. Currently CONFLICTING against main and was never reviewed/merged. Needs a rebase and full review.
9 | Security | Epic: Advanced Authentication & Security Enhancements | Medium | Epic / not started | Issue #76 (open) | MFA/TOTP (Google/Microsoft Authenticator, recovery codes), bot protection (reCAPTCHA/Turnstile) on login/register/forgot-password, real email verification service with templates/queue/retry, device fingerprinting + new-device/suspicious-login alerts, security notification emails. No work started.
10 | Security | Epic: Advanced Platform Security, Monitoring & Compliance | Medium | Epic / not started | Issue #77 (open) | Security dashboard + failed-login analytics, SIEM export (syslog/ELK/Splunk/Sentinel), threat intel (IP reputation, GeoIP, VPN/TOR detection), API key management + abuse detection, GDPR tooling (data export, right-to-delete, consent, privacy audit logs), automated DB backup + restore validation, scheduled dependency/secret/container scans. No work started.
11 | Security | toggleProgramInstructor admin endpoint has no audit log entry | Low | Blocked | PR #111 (unmerged) | Sibling sensitive admin actions (toggleBlockUser, changeUserRole) call the audit-log helper (userId/targetId/severity/metadata); the new program-instructor toggle endpoint does not. Correctly gated to admin/superadmin via the router, just missing the log entry.
12 | Security | Encoding corruption (UTF-8 BOM + mojibake) in two backend files | Low | Blocked | PR #111 (unmerged) | server/models/User.js and server/controllers/adminController.js each got a stray UTF-8 BOM prepended and every em-dash in comments mangled to â€”. Comments only, no functional impact, but signals the dev's local tooling is corrupting files it touches — worth asking the author to fix their script.
13 | Security | Forgot-password rate limiters defined but wired to nothing | Low | Open | Predecessor audit, re-verified this session | Correctly out of scope per CLAUDE.md (no forgot-password flow), but the forgot-password/OTP rate limiter configs still exist unused in the codebase — dead scaffolding worth removing for clarity, or wiring up if the feature ever gets built.
14 | Security | getCourseById isAdmin check only tests role==='admin', not 'superadmin' | Low | Open | Predecessor audit, re-verified this session | courseController.js:254. Minor inconsistency — a superadmin viewing a non-approved course's details may be treated as a non-privileged viewer depending on the rest of the gating logic. Not a security hole (superadmins aren't blocked elsewhere), just an inconsistent check worth tidying.
15 | Security | Cookies / password hashing / JWT secret / input sanitization / CORS / error handling | Low | Verified OK | Predecessor audit + spot-checked this session | httpOnly cookies, bcrypt cost 12 with select:false, JWT secret from env, global mongo-sanitize + XSS middleware, env-driven CORS allowlist, and the production error handler (never leaks stack traces/DB internals to the client, logs full detail server-side via Winston) — all confirmed sound, no regressions from anything merged this session.
16 | Security | Full route-level auth sweep — no unprotected mutating endpoint found | Low | Verified OK | Done this session in response to a direct question about security completeness | Grepped every POST/PUT/PATCH/DELETE across every file in server/routes/ and confirmed each is gated by protect (and authorize(...) where role-restricted), either inline or via a router.use(protect, authorize(...)) guard at the top of the file (adminRoutes, systemConfigRoutes, websiteRoutes). instructorRoutes is intentionally GET-only/public. No gaps found.
17 | Security | CSRF double-submit cookie check — verified real and correctly scoped | Low | Verified OK | Done this session | authMiddleware.js's protect middleware compares the non-httpOnly csrfToken cookie against an X-CSRF-Token header on every POST/PUT/PATCH/DELETE and rejects with 403 on mismatch — a real, working double-submit CSRF defense, not just a cookie being set with nothing checking it.
18 | Security | File upload validation — verified real (size limits + mimetype filtering) | Low | Verified OK | Done this session | server/middleware/upload.js enforces per-type size limits (500MB video / 5MB image / 20MB document) and a fileFilter rejecting mismatched mimetypes for all three upload routes, with a wrapper that turns multer errors into proper 400s instead of a generic 500.
19 | Security | Register endpoint role restriction — verified server-enforced | Low | Verified OK | Done this session | authController.js computes safeRole server-side (role === 'instructor' ? 'instructor' : 'student') and ignores any other client-supplied role value — a public registration request cannot self-elevate to admin/superadmin.
20 | Security | No secrets ever committed to git history | Low | Verified OK | Done this session | git log --all over server/.env returns no history — the real .env file has never been committed. .gitignore correctly excludes .env/.env.local/.env.* while allow-listing .env.example.
21 | Backend | LearningPortal.jsx crashes on undefined `isActive` | Critical | Open | Predecessor audit, re-verified this session (still present on current main) | LearningPortal.jsx:474-475 references `isActive`, which is never declared in scope — the correct variable is `isCurrent`, declared at line 418. Throws a ReferenceError on any course with lessons, taking down the entire video-lesson viewing flow for students. One-line fix (rename to isCurrent). Not touched by any PR merged this session.
22 | Backend | Cloudinary credentials are still literal placeholders | Critical | Open | Predecessor audit, re-verified this session | server/.env has CLOUDINARY_API_KEY=your_api_key etc. — all video/image uploads are non-functional until real credentials are set. Environment-specific, not a code bug, but blocks everything downstream of course/lesson creation.
23 | Backend | Admin approve-course sets status:'published', not 'approved' | Medium | Open | Predecessor audit, re-verified this session (still present on current main) | AdminCourseManagementTab.jsx:197 — handleApprove writes status:'published', which matches neither the 'Approved' nor 'Pending' filter tab (the real Course.status enum is pending/approved/rejected). Approved courses vanish from the admin list until a manual page refresh. Different bug from the filter-crash PR #92 already fixed — do not conflate the two.
24 | Backend | Scope decision: Course/Lesson admin management schema mismatch | High | Needs decision | Issue #59 (open) | A separate unmerged PR lineage (#56) uses a draft/published/archived/hidden/rejected status vocabulary and a Lesson→Section schema migration that doesn't match main's actual pending/approved/rejected model and direct Lesson.course reference. Needs either a rewrite against the current schema or an explicit, reviewed Section migration — not a casual merge.
25 | Backend | Scope decision: Website Management module | Medium | Needs decision | Issue #60 (open) — partially superseded by PR #107 | Full CMS (homepage hero/banner, About/FAQ/Contact/Testimonials editors) with a ConfigProvider wrapping the whole app. PR #107's Landing Page CMS shipped part of this already this session — re-check what #60 still covers that #107 doesn't before scoping further work.
26 | Backend | Scope decision: System Management / maintenance lock / registration gating | High | Needs decision | Issue #61 (open) | Touches the login/register path directly (config-driven maintenance lock, .edu email gating, config-driven JWT expiry) — CLAUDE.md explicitly flags backend auth as reviewed/stable and asks to check before changing it. Needs its own focused review, not a bundled dashboard PR.
27 | Backend | Scope decision: revenue/commission-split logic presents fabricated financial data | High | Needs decision | Issue #62 (open) + PR #111 | CommissionSlider.jsx + per-enrollment platformCommission/instructorShare computation exists with no real payment processor behind it — CLAUDE.md says no payments/Stripe, price is display-only. Needs a decision: scope in real payments properly, or drop the fabricated-accounting UI. PR #111 compounds this by hardcoding the split (see Security sheet row above).
28 | Backend | AdminOverviewTab dashboard stats have hardcoded fallback numbers | Medium | Open | Predecessor audit, not touched by any merged PR | AdminOverviewTab.jsx:51-59 masks genuine zero-values with hardcoded fallback numbers — an admin could see plausible-looking stats that aren't real.
29 | Backend | Course.semester has no bounds validation | Low | Open | Predecessor audit, re-verified this session | Plain Number with no min/max/enum — an instructor could set 0, -5, or 9999. Not exploitable, just a silent data-quality gap (course would never appear in any Home semester row).
30 | Backend | sendTestEmail backend endpoint is fully fake | Low | Open | Predecessor audit, re-verified this session | systemConfigController.js — setTimeout(800) then a hardcoded success response; comment literally says "In a real app, we would use Nodemailer + SendGrid here."
31 | Backend | AdminPortal.jsx has dead i18n code (toggleLanguage/t declared, never wired) | Low | Open | Found during PR #94 merge this session | A language-toggle handler and `t` are declared in AdminPortal.jsx's top-level scope but no button in the file calls them — leftover from an earlier, apparently-reverted admin i18n pass. Confirmed pre-existing on origin/main before this session's merges, not something introduced by them.
32 | Frontend | Epic: Mobile responsiveness | High | Epic / not started | Issue #86 (open) | The entire platform is desktop-only. Full checklist: convert fixed sidebar to bottom nav/drawer under 768px, stack Explore/Dashboard grids to 1 column, 44×44px touch targets, collapse search bar, full-screen/bottom-sheet modals for dropdowns, horizontally-scrollable category pills. No work started.
33 | Frontend | Epic: Admin/SuperAdmin portal styling refresh | Medium | Epic / not started | Issue #63 (open) — check overlap with PR #94 first | Collapsible sidebar, redesigned overview stats with role-based accent colors, improved filtering/table UX, light-mode fixes. PR #94 (merged this session) already delivered light-mode support and table/pagination fixes across Admin — re-scope this issue against current main before starting, likely smaller than originally written.
34 | Frontend | Ongoing UI/UX micro-interaction polish (open-ended) | Low | Open | Issue #23 (open) | No concrete remaining action items — author's last update says "standing by for the next set of feature requests." Keep open as a catch-all or close and re-open specific issues as needed.
35 | Frontend | No shared 401/session-expiry handling | Medium | Open | Issue #21 | api/axios.js has no response interceptor — an expired session cookie surfaces as a generic inline error per component instead of redirecting to /auth. A single interceptor would fix every call site at once.
36 | Frontend | No AbortController/cleanup in several data-fetching effects | Low | Open | Issue #21 | CoursePage.jsx, LearningPortal.jsx, DashboardTab.jsx — rapid navigation can set state after the component has unmounted.
37 | Frontend | InstructorPortal/AdminPortal flash protected UI before role-redirect | Low | Open | Issue #21 | Both only redirect wrong-role users after mount, so there's a brief flash of the protected screen before the redirect fires.
38 | Frontend | Inconsistent error UX (inline div vs. alert()) | Low | Open | Issue #21 | Some flows show an inline error <div>, others (e.g. AdminPortal.jsx) use a blocking alert() — should standardize on one pattern.
39 | Frontend | console.log('[MOCK EMAIL]...') left in CheckoutPage.jsx | Low | Open | Issue #21 | Leftover debug logging tied to the checkout flow that's already flagged as needing a scope decision (see Backend sheet row).
40 | Frontend | Several dead buttons/links with no handler | Low | Open | Issue #21 | "Explore Catalog" hero button, "View all" href="#", "Profile"/"Settings" href="#" in TopNav, search input with no onChange, "Get Certificate"/"Ask a Question" buttons in LearningPortal.
41 | Frontend | LearningPortal shows identical filler text + fake PDF download for every lesson | Low | Open | Issue #21 | Hardcoded placeholder content and a non-functional download link appear under every lesson regardless of its actual content.
42 | Frontend | Placeholder Unsplash/Pravatar images presented as real course art | Low | Open | Issue #21 | data.js fallback thumbnails/avatars used in CheckoutPage and elsewhere look like real content but are generic placeholder images.
43 | Frontend | "Remember Me" checkbox is decorative | Low | Open | CLAUDE.md known non-blocking issue | UI exists on the login form but isn't wired to any actual session-persistence behavior difference.
44 | Frontend | Stray unrelated files committed to main (PDFs + Python script) | Low | Open | Found via PR #94 merge this session | Program_Premium_Deck.pdf, Program_Presentation_Blueprint.pdf, and pdf/pdf.py landed on main through PR #94's merge — personal/marketing files with nothing to do with the app. Safe to delete.
45 | Frontend | SettingsPage "Change picture" button: invisible text on hover in dark mode | Low | Open | Found during PR #94 merge this session | Hover state forces the button background to pure white while the text color stays var(--text-primary), which is also white in dark mode — text disappears on hover. Pre-existing in PR #94's own code, not introduced by the merge.
46 | Frontend | Two leftover physical CSS properties break RTL mirroring | Low | Open | Found during PR #102 review this session | App.css .ticks (border-left/right-color) and content.css .phone-input-wrapper .phone-prefix (border-right) were missed during the logical-properties conversion — colored edges/dividers land on the wrong side in Arabic.
47 | Frontend | Cross-portal language leak on a portal's first-ever visit | Low | Open | Found during PR #105 review this session | Per-portal language scoping only restores a portal's own saved localStorage preference; a portal that has never saved its own preference doesn't reset from whatever language i18next is currently set to, so a language toggled in one portal can leak into another on its first visit.
48 | Frontend | Frontend CSS/theme values may not perfectly match original design intent | Low | Open | CLAUDE.md known non-blocking issue | General note carried in project docs — no specific repro, listed for completeness.
49 | Testing | Zero frontend test coverage | High | Open | Gap identified this session | No Vitest/Jest/React Testing Library/Cypress/Playwright installed anywhere in client/. The only automated test in the whole repo is server/test-integration.js (backend, integration-level). Every frontend regression currently relies entirely on manual QA or `npm run build` (which only catches syntax errors, not logic bugs).
50 | Testing | No full structured QA pass over every role's entire UI | Medium | Open | Predecessor audit, still true | All manual QA done across sessions has been targeted at whatever feature was being changed, never a systematic click-through of every existing screen for every role.
51 | Testing | Real Cloudinary upload never verified end-to-end | Medium | Open | Predecessor audit, still true | Blocked by the placeholder-credentials issue above — can't be tested until real credentials exist somewhere.
52 | Testing | server/test-integration.js passes on current main | Low | Verified OK | Re-run this session | All assertions pass against current main (post PR #92/93/94/101/102/105/107/109/110 merge). Regression-clean for the flows it covers: register → create course → approve → enroll → mark complete → verify progress.
53 | Testing | `npm run build` passes on current main | Low | Verified OK | Re-run this session | Zero errors. Bundle warns about a >500KB chunk (1.2MB / 315KB gzip) — not an error, but worth a code-splitting pass eventually.
54 | Deployment | No persistent deployment anywhere | High | Open | Predecessor audit, still true | No GitHub Deployments/Pages, no Dockerfile, no vercel.json/render.yaml/Procfile/netlify.toml anywhere in the repo. The app has never been run outside a local dev environment.
55 | Deployment | No CI/CD | High | Open | Predecessor audit, still true — confirmed relevant again this session | No .github/workflows directory. Nothing runs build/lint/tests automatically on a PR. This session found a live security regression (gutted rate limiter) sitting in an open, GitHub-reported-mergeable PR (#111) with nothing to catch it before a human review did.
56 | Deployment | server/.env.example port drift | Low | Open | Predecessor audit, re-verified this session | server/.env.example still defaults PORT=5000; the actual local dev value in server/.env is 5050. Cosmetic but will confuse the next person setting up the project from scratch.
57 | Deployment | CORS/cookie behavior never exercised against a real production domain | Medium | Open | Predecessor audit, still true | Code is written correctly (env-driven allowlist, secure/sameSite=none only in production) but has literally never run against a deployed frontend domain since nothing is deployed.
58 | Deployment | No backup / disaster-recovery process for the database | Medium | Open | Gap identified this session (also part of Issue #77's larger scope) | No automated MongoDB backup, restore-validation, or documented DR procedure exists at any scale, including the current MVP.
59 | Open PRs | PR #104 "Backup workspace" should be closed | Low | Open | Reviewed this session | Not a real PR — empty description, duplicates commits already in #101/#102, includes an unrelated PDF deck and a pdf-generation script. Recommend closing without merging.
60 | Open PRs | PR #111 blocked pending fixes | High | Blocked | Reviewed this session | Feature work (PROGRAM instructor badge, 18-major i18n, tooltips) is otherwise reasonable, but blocked on: reverting the gutted login rate limiter, a decision on the hardcoded commission-split logic, and cleanup of the stray Python/CJS scripts + git-log dump (add_props.py, apply_animations*.py, fix_logos*.py, history.txt, etc.) committed alongside it.
61 | Open PRs | PR #82 needs rebase + review | High | Blocked | Reviewed this session | Currently CONFLICTING against main. Contains genuinely valuable security work (see Security sheet) that nothing else in the current backlog covers — worth prioritizing the rebase.